## Hoja1
Team .. | Orion Mission | 2022-07-03
Hazard | Possible Causes | Risk of Mishap and Rationale | Mitigation Approach | Risk of Injury after Mitigation
Ignition failure | Igniter does not fire | Medium. Electronic circuit does not function properly | 1) Test ignition device before launch until reduce errors at minimum 2) Standardize ignition procedure | Low.
Unstable rocket after liftof | Center of pressure over center of gravity | Low. Discordance between theoretical and real model | 1) Verify liftoff weight after manufacturing rocket 2) Verify center of mass position after manufacturing rocket | Low
Motor pops out from rocket airframe | Weak thrust retention | Medium. Bad design of thrust retention plate. | 1) Resistance calculation of thrust retention plate | Low.
Free fall of rocket | Parachute is not ejected or is misfunctioning | Medium. Lack of redundancy in electronic devices and tests. | 1) Apply redundancy algorithms for deploying parachute 2) Test deployment hardware for reducing possible mistakes | Low
Team .. | Orion Mission | 2022-07-03
Risk | Possible Causes | Risk of Mishap and Rationale | Mitigation Approach | Low.
Motor ignition before launch near people | Accidental source of heat near motor storage | Low. Lack of protocol for propellant storage | 1) Warning marks 2) Predefined place and mode of storage | Low.
People around an unstable rocket after liftof | Center of pressure over center of gravity | Low. Discordance between theoretical and real model | 1) Follow procedures established for LASC related to distance between launchpad and people at the event 2) Add a condition to the algorithm for activating deployment hardware if rocket presents high angles of attack | Low.
Rocket airframe or motor fall over people | Weak mechanical resistance of pieces or parachute does not open | Medium. Bad design procedures | 1) Verify engineering calculations 2) Test rocket airframe resistance 3) Safeguard people under marquees